## Phase 1 Milestones
CONNECT CRM — PHASE 1 IMPLEMENTATION BREAKDOWN
Milestone 1.1 (Multi-Tenant Foundation & Operations) & Milestone 1.2 (AWS S3 Media Pipeline & Client Approval Portal)
Milestone | Module ID | Module Name | Feature / Sub-Task | What We Have to Do (Scope & Deliverable) | How We Are Going to Do That (Technical Execution) | Component / Layer | Target Users
Milestone 1.1 | Module-A | Auth & RBAC Module | Two Distinct Portals (Agency vs Client) | Strict separation between the Main Agency CRM Portal (Full access, team tracking, client management) and the Client Portal (Strictly read/suggest/approve own calendar only). | Role-based routing and domain isolation. Clients have ZERO access to internal team stats, assignments, or other clients' calendars. | Security & RBAC | Agency Team & Clients
Milestone 1.1 | Module-A | Auth & RBAC Module | Dedicated Client Login | Enable dedicated client login portals (e.g. Nelson Luxe, Kohinoor TEZ) with individual credentials and brand logos. | Auth.js / NextAuth session management with organization domain routing and password encryption. | Security & Frontend | Client Reviewers
Milestone 1.1 | Module-B | Client & Quota Engine | Client Creation & Quota Allocation | Agency creates client profile (e.g. Nelson Luxe, Kohinoor) and sets monthly deliverables (Creatives: 15-30, Reels: 10-20, Stories: 30) plus client requirements. | Clients table in PostgreSQL storing brand metadata, active contracts, and tenant subdomain configuration. | Backend & DB | Agency PM & Lead
Milestone 1.1 | Module-C | Native Calendar Creator | 1-Click 'Create Calendar' Flow | Inside client profile, click 'Create Calendar' -> select Month & Year (e.g. Oct 2026) -> automatically initialize 30/31-day scheduling grid. | Dynamic calendar initialization service that generates daily schedule slots with correct dates, days of the week, and status=DRAFT. | Core Feature | Agency Strategists & PM
Milestone 1.1 | Module-C | Native Calendar Creator | Day-by-Day Post Builder | Natively build each post: Select Date, add Special Day, assign Content Pillar, choose Type (IMAGE, REEL, Carousel, Story), write Visual Brief, Reel Bytes, and Captions. | Interactive form modal and slide-out drawer with auto-save, rich text editor, character counter, and hashtag manager. | Frontend & API | Strategists & Copywriters
Milestone 1.1 | Module-D | Team Workload & Tracking | Admin Team Productivity Dashboard | Track how much work each internal team member has completed this month across all clients (e.g. Designer A: 25/30 creatives done; Editor B: 12/15 reels finished). | Aggregation service querying tasks by assignee_id and month; renders workload progress bars and completed vs pending counts. | Admin Dashboard | Team Lead & Project Mgr
Milestone 1.1 | Module-D | Team Workload & Tracking | Team Member 'My Tasks' Board | Individual team members (Designers, Editors, Copywriters) log into the Main CRM and see their personal task board for the month across all assigned clients. | Task list / Kanban filtered by user_id with statuses (To Do, In Progress, Submitted for QA, Done) and direct links to post cards. | Internal Operations | Designers, Editors, Copywriters
Milestone 1.1 | Module-D2 | Client View Simulator | 'Preview as Client' Mode | Before publishing/sharing calendar with client, agency team can click 'Preview as Client' to verify exactly how it will appear on client portal. | Impersonation/Preview mode toggling the Client Portal UI view within the agency workspace without affecting live client data. | Frontend Quality Tool | Team Lead & Account Mgr
Milestone 1.2 | Module-E | S3 Cloud Media Engine | Direct Browser-to-S3 Uploads | Designers and editors upload 4K Reels (MP4/MOV) and images directly without overloading the application server. | AWS S3 SDK generating presigned PUT URLs with multipart chunking; client browser uploads directly to S3 bucket. | Cloud Infrastructure | Designers & Video Editors
Milestone 1.2 | Module-E | S3 Cloud Media Engine | Zero-Friction Media Streaming | Completely eliminate Google Drive 'Access Denied' errors by streaming media directly inside the portal. | Generate time-limited (2-hour expiry) presigned GET URLs streamed via AWS CloudFront CDN with byte-range video support. | Cloud Infrastructure | Client Reviewers & Team
Milestone 1.2 | Module-E | S3 Cloud Media Engine | In-Portal Rich Media Player | Custom in-browser media preview: frame-by-frame scrubbing for Reels, swipeable multi-slide carousel viewer, high-res lightbox. | HTML5 Custom Video Player component with speed/scrubbing controls + Swiper.js carousel slider component for multi-slide posts. | Frontend Components | Client Reviewers & Team
Milestone 1.2 | Module-F | Client Collaboration Portal | Client-Only Isolated Calendar View | Dedicated, branded portal where client only sees their own calendar, plays videos/reels, reads captions, and tracks deliverable totals. | Responsive, mobile-optimized Next.js layout restricted strictly to the authenticated client's company data (Zero view of internal team stats). | Client Frontend | Client Stakeholders
Milestone 1.2 | Module-G | Approval State Machine | Specific Item Suggestion / Change Request | Clients can click on any specific post and submit change suggestions/revisions (e.g. 'Update doctor name in slide 2', 'Change reel background audio'). | Item-level feedback thread recording suggestion text, timestamp, and client user ID, notifying the assigned designer/copywriter. | Backend & Frontend | Clients & Agency Team
Milestone 1.2 | Module-G | Approval State Machine | 1-Click Post & Batch Approval | Clients can approve individual posts or the entire weekly/monthly batch with a single green check button. | Atomically locks approved calendar items, updates status to APPROVED, and records digital audit approval timestamp. | Backend & State Engine | Client Stakeholders
Milestone 1.2 | Module-H | Notification Webhooks | Automated Approval & Feedback Alerts | Instantly notify agency team when client requests changes or approves, and notify client when calendar is ready. | Transactional email service (Resend / SendGrid) + WhatsApp Business / Slack webhook notifications on state change events. | Integrations & Alerts | Agency & Client Leads

## Team Target Playbook
SOCIAL MEDIA TEAM OPERATIONAL PLAYBOOK & WORKLOAD TRACKING
Phase 1: Internal Team Workload Management vs Client-Facing Suggestion & Approval Operations
Stage | Timeline in Month | Responsible Role | Portal View (Main CRM vs Client Portal) | Action & Workflow Details | Deliverable & Output | Productivity / Tracking Impact
Stage 1: Setup & Assign | Days 1–2 | Agency Admin / PM | Main CRM Portal (Admin View) | Creates Client Profile (Nelson, Kohinoor, etc.), sets monthly targets (30 creatives, 20 reels), creates 'October 2026' calendar, and assigns team members (Strategist, Copywriter, Designer, Video Editor). | Client Profile & Calendar initialized with assigned team members. | Team assignments established; initial workload distribution calculated.
Stage 2: Strategy & Tasks | Days 2–4 | Content Strategist (e.g. Prerna) | Main CRM Portal (Planner View) | Maps 31-day calendar with Content Pillars, Festivals, Reel Hooks, and assigns specific post tasks to designated copywriters and designers. | Full month content backbone planned with individual task tickets. | Guarantees required number of posts are scheduled to hit the quota.
Stage 3: Task Board Execution | Days 3–8 (Batch 1) | Copywriters, Designers, Editors | Main CRM Portal ('My Tasks' Board) | Team members open their personal 'My Tasks' dashboard. Copywriters draft Reel Bytes & Captions. Designers/Editors view visual briefs and drag-and-drop PNGs/MP4s straight into S3. | Drafts, high-res graphics, and 4K MP4 Reels linked to calendar items. | Admin tracks real-time progress: e.g. Designer A: 15/20 posts completed; Editor B: 8/10 reels completed.
Stage 4: Workload Monitoring | Days 5–15 (Ongoing) | Team Lead / PM | Main CRM Portal (Workload Dashboard) | Admin monitors live productivity meters: sees how many tasks each team member has completed vs pending. Reallocates tasks if any editor or designer is falling behind. | Live Team Performance Matrix across all clients. | Prevents team burnout and ensures no client calendar gets delayed.
Stage 5: Preview & QA | Days 8–9 | Team Lead / Account Manager | Main CRM Portal ('Preview as Client') | Toggles 'Preview as Client' to verify the exact client experience without logging into a test account. Verifies video player, slides, and copy. Clicks 'Submit to Client'. | Calendar status moves to SHARED_WITH_CLIENT. WhatsApp/Email alert sent. | Zero-defect assurance before client ever sees the posts.
Stage 6: Client Review & Suggestion | Days 9–12 | Client Reviewer (e.g. Nelson/Kohinoor) | Client Portal ONLY (Isolated Branded View) | Client logs into their branded portal (e.g. nelson.zkconnect.io). Client only sees their calendar and media. Clicks on a specific post to give suggestions/changes or clicks 1-Click Approve. | Specific suggestions tagged to the post card (No view of internal team stats). | Direct client feedback routed straight to the assigned designer/copywriter.
Stage 7: Revision & Approval Lock | Days 11–14 | Designer/Copywriter & Client | Both Portals (Collaborative Loop) | Assigned designer updates the creative based on client suggestion and re-uploads (v2) to S3. Client reviews v2 and clicks 'Approve'. Post is locked. | Post status locked to APPROVED with digital timestamp. | Eliminates infinite revision cycles and resolves client requests in hours.
Stage 8: Final Quota & Delivery | Scheduled Dates (All Month) | Social Media Manager | Main CRM Portal (Publishing Command) | Social media team posts approved assets and marks status PUBLISHED in CRM. Monthly deliverable meter reaches 100% (TARGET COMPLETED). | All contracted deliverables published accurately on client social accounts. | 100% Monthly Target Achieved across all clients with full productivity audit.